## project schedule
Task ID | Predecessor | Name | Duration (days)
A | 0 | Building layout | 20
B | A | Interior design | 20 |  | 750
C | B | Decoration | 10
D | C | Stakeholder agreement | 30
E | D | Labor contract | 25
F | E | Copyright licensing | 25
G | F | Business certification | 30
H | G | Suppliers | 30
I | H | Exhibition Hall | 25 | 5
J | H | Restaurant | 20 | 10
K | H | Souvenir Shop | 30
L | K | Conference Hall | 15
M | K | Theaters | 20
N | M | Learning Hub | 30
O | N | Artifacts | 125 | 55
P | O | 3D Technology | 70 | 110
Q | P | Paintings | 100 | 80
R | Q | Virtual models | 115 | 65
S | R | Facilities | 160 | 20
T | S | Documentaries | 110 | 70
U | T | Books | 125 | 55
V | U | Posters | 160 | 20
W | V | Pictures | 180
X | W | Relaxing facilities | 150 | 30
Y | X | Pedestrian areas | 95
Z | Y | Car parking | 100
AA | W | Bus stop | 90
X

## network diagram
[36 empty] | 285 | O | 410
[36 empty] | 55 | Artifacts
[36 empty] | 340 | 125 | 465
[36 empty] | 285 | P | 355
[36 empty] | 110 | 3D Technology
[36 empty] | 395 | 70 | 465
[36 empty] | 285 | Q | 385
[36 empty] | 80 | Paintings
[36 empty] | 365 | 100 | 465
[36 empty] | 285 | R | 400
[24 empty] | 190 | I | 215 | [9 empty] | 65 | Virtual models
[24 empty] | 5 | Exhibition Hall | [10 empty] | 350 | 115 | 465
[24 empty] | 195 | 25 | 220
[36 empty] | 285 | S | 445
0 | A | 20 | 20 | B | 40 | 40 | C | 50 | 50 | D | 80 | 80 | E | 105 | 105 | F | 130 | 130 | G | 160 | 160 | H | 190 | 190 | J | 210 | 220 | L | 235 | 235 | M | 255 | 255 | N | 285 | 20 | Facilities |  | 465 | Y | 560 | 560 | Z | 660 | 660 | AA | 750
0 | Building Layout |  | 0 | Interior Design |  | 0 | Decoration |  | 0 | Stakeholder Agreement |  | 0 | Labor Contract |  | 0 | Copyright licensing |  | 0 | Business certification |  | 0 | Suppliers |  | 10 | Restaurant |  | 0 | Conference Hall |  | 0 | Theaters |  | 0 | Learning Hub |  | 305 | 160 | 465 | 0 | Pedestrian Areas |  | 0 | Car Parking |  | 0 | Bus Stop
0 | 20 | 20 | 20 | 20 | 40 | 40 | 10 | 50 | 50 | 30 | 80 | 80 | 25 | 105 | 105 | 25 | 130 | 130 | 30 | 160 | 160 | 30 | 190 | 200 | 20 | 220 | 220 | 15 | 235 | 235 | 20 | 255 | 255 | 30 | 285 |  |  |  | 465 | 95 | 560 | 560 | 100 | 660 | 660 | 90 | 750
[36 empty] | 285 | T | 395
[24 empty] | 190 | K | 220 | [9 empty] | 70 | Documentaries
[24 empty] | 0 | Souvenir Shop | [10 empty] | 355 | 110 | 465
[24 empty] | 190 | 30 | 220
[36 empty] | 285 | U | 410
|  |  |  | Critical path = A, B, C, D, E, F, G, H, K, L, M, N, W, Y, Z, AA | [31 empty] | 55 | Books
|  |  |  | Normal project duration = 20 + 20 + 10 + 30 + 25 + 25 + 30 + 30 + 30 + 15 + 20 + 30 + 95 + 100 + 90 + 180 = 750 | [31 empty] | 340 | 125 | 465
[36 empty] | 285 | V | 445
[36 empty] | 20 | Posters
[36 empty] | 305 | 160 | 465
[36 empty] | 285 | W | 465
[36 empty] | 0 | Pictures
[36 empty] | 285 | 180 | 465
[36 empty] | 285 | X | 435
[36 empty] | 30 | Relaxing Facilities
[36 empty] | 315 | 150 | 465